## production_orders
order_id | product_type | quantity | planned_start | planned_end | actual_start | actual_end | total_planned_hours | total_actual_hours | order_status
ORD-001 | Product A | 40 | 2026-02-02 08:00 | 2026-02-09 | 2026-02-02 08:00 | 2026-02-10 08:00 | 160 | 192 | delayed
ORD-002 | Product C | 20 | 2026-02-03 08:00 | 2026-02-08 08:00 | 2026-02-03 08:00 | 2026-02-09 06:48 | 120 | 142.8 | delayed
ORD-003 | Product B | 20 | 2026-02-04 08:00 | 2026-02-08 12:00 | 2026-02-04 08:00 | 2026-02-08 17:00 | 100 | 105 | on-time
ORD-004 | Product A | 60 | 2026-02-05 08:00 | 2026-02-15 08:00 | 2026-02-05 08:00 | 2026-02-15 12:48 | 240 | 244.8 | on-time
ORD-005 | Product B | 40 | 2026-02-06 08:00 | 2026-02-14 16:00 | 2026-02-06 08:00 | 2026-02-17 04:00 | 200 | 260 | delayed
ORD-006 | Product A | 40 | 2026-02-09 08:00 | 2026-02-16 | 2026-02-09 08:00 | 2026-02-16 04:48 | 160 | 164.8 | on-time
ORD-007 | Product C | 15 | 2026-02-10 08:00 | 2026-02-14 02:00 | 2026-02-10 08:00 | 2026-02-14 05:09 | 90 | 93.15 | on-time
ORD-008 | Product A | 25 | 2026-02-11 08:00 | 2026-02-15 12:00 | 2026-02-11 08:00 | 2026-02-15 07:00 | 100 | 95 | on-time
ORD-009 | Product B | 45 | 2026-02-12 08:00 | 2026-02-21 17:00 | 2026-02-12 08:00 | 2026-02-23 18:30 | 225 | 274.5 | delayed
ORD-010 | Product B | 35 | 2026-02-13 08:00 | 2026-02-20 15:00 | 2026-02-13 08:00 | 2026-02-20 06:15 | 175 | 166.25 | on-time
ORD-011 | Product A | 40 | 2026-02-16 08:00 | 2026-02-23 | 2026-02-16 08:00 | 2026-02-23 02:24 | 160 | 162.4 | on-time
ORD-012 | Product C | 60 | 2026-02-17 08:00 | 2026-03-04 08:00 | 2026-02-17 08:00 | 2026-03-08 09:12 | 360 | 457.2 | delayed
ORD-013 | Product B | 15 | 2026-02-18 08:00 | 2026-02-21 11:00 | 2026-02-18 08:00 | 2026-02-21 10:38 | 75 | 74.625 | on-time
ORD-014 | Product A | 20 | 2026-02-19 08:00 | 2026-02-22 16:00 | 2026-02-19 08:00 | 2026-02-22 15:36 | 80 | 79.6 | on-time
ORD-015 | Product A | 30 | 2026-02-20 08:00 | 2026-02-25 08:00 | 2026-02-20 08:00 | 2026-02-26 05:36 | 120 | 141.6 | delayed
ORD-016 | Product B | 35 | 2026-02-23 08:00 | 2026-03-02 15:00 | 2026-02-23 08:00 | 2026-03-02 22:00 | 175 | 182 | on-time
ORD-017 | Product A | 36 | 2026-02-24 08:00 | 2026-03-02 08:00 | 2026-02-24 08:00 | 2026-03-02 09:26 | 144 | 145.44 | on-time
ORD-018 | Product A | 10 | 2026-02-25 08:00 | 2026-02-27 | 2026-02-25 08:00 | 2026-02-27 09:36 | 40 | 49.6 | delayed
ORD-019 | Product C | 60 | 2026-02-26 08:00 | 2026-03-13 08:00 | 2026-02-26 08:00 | 2026-03-13 06:34 | 360 | 358.56 | on-time
ORD-020 | Product A | 5 | 2026-02-27 08:00 | 2026-02-28 04:00 | 2026-02-27 08:00 | 2026-02-28 08:24 | 20 | 24.4 | delayed
ORD-021 | Product B | 50 | 2026-03-02 08:00 | 2026-03-12 18:00 | 2026-03-02 08:00 | 2026-03-12 17:00 | 250 | 249 | on-time
ORD-022 | Product A | 25 | 2026-03-03 08:00 | 2026-03-07 12:00 | 2026-03-03 08:00 | 2026-03-07 08:00 | 100 | 96 | on-time
ORD-023 | Product B | 30 | 2026-03-04 08:00 | 2026-03-10 14:00 | 2026-03-04 08:00 | 2026-03-12 05:00 | 150 | 189 | delayed
ORD-024 | Product A | 60 | 2026-03-05 08:00 | 2026-03-15 08:00 | 2026-03-05 08:00 | 2026-03-15 03:12 | 240 | 235.2 | on-time
ORD-025 | Product C | 10 | 2026-03-06 08:00 | 2026-03-08 20:00 | 2026-03-06 08:00 | 2026-03-18 20:00 | 60 | 300 | delayed
ORD-026 | Product A | 10 | 2026-03-09 08:00 | 2026-03-11 | 2026-03-09 08:00 | 2026-03-10 22:00 | 40 | 38 | on-time
ORD-027 | Product B | 30 | 2026-03-10 08:00 | 2026-03-16 14:00 | 2026-03-10 08:00 | 2026-03-16 11:00 | 150 | 147 | on-time
ORD-028 | Product C | 20 | 2026-03-11 08:00 | 2026-03-16 08:00 | 2026-03-11 08:00 | 2026-03-17 02:00 | 120 | 138 | delayed
ORD-029 | Product B | 50 | 2026-03-12 08:00 | 2026-03-22 18:00 | 2026-03-12 08:00 | 2026-03-23 04:00 | 250 | 260 | on-time
ORD-030 | Product C | 25 | 2026-03-13 08:00 | 2026-03-19 14:00 | 2026-03-13 08:00 | 2026-03-20 14:00 | 150 | 174 | delayed
Formulas:
planned_end = [planned_start]+([total_planned_hours]/24)
actual_end = [planned_start]+([total_actual_hours]/24)

## production_stages
order_id | stage_name | machine_id | operator_id | planned_time_min | actual_time_min | delay_min | rework
ORD-001 | Cutting | M-01 | OP-04 | 1920 | 1977.6 | 57.6 | No
ORD-001 | Welding | M-04 | OP-02 | 2880 | 3225.6 | 345.6 | Yes
ORD-001 | Assembly | M-05 | OP-02 | 3360 | 3460.8 | 100.8 | Yes
ORD-001 | Finishing | M-06 | OP-02 | 1440 | 1468.8 | 28.8 | No
ORD-002 | Cutting | M-01 | OP-03 | 1440 | 1512 | 72 | Yes
ORD-002 | Welding | M-03 | OP-02 | 2160 | 2376 | 216 | Yes
ORD-002 | Assembly | M-05 | OP-07 | 2520 | 2570.4 | 50.4 | No
ORD-002 | Finishing | M-06 | OP-03 | 1080 | 1101.6 | 21.6 | No
ORD-003 | Cutting | M-01 | OP-06 | 1200 | 1212 | 12 | No
ORD-003 | Welding | M-04 | OP-06 | 1800 | 1818 | 18 | No
ORD-003 | Assembly | M-05 | OP-06 | 2100 | 2142 | 42 | No
ORD-003 | Finishing | M-06 | OP-04 | 900 | 909 | 9 | No
ORD-004 | Cutting | M-02 | OP-07 | 2880 | 2908.8 | 28.8 | No
ORD-004 | Welding | M-03 | OP-02 | 4320 | 4363.2 | 43.2 | No
ORD-004 | Assembly | M-05 | OP-05 | 5040 | 5040 | 0 | No
ORD-004 | Finishing | M-06 | OP-06 | 2160 | 2160 | 0 | No
ORD-005 | Cutting | M-02 | OP-03 | 2400 | 2640 | 240 | Yes
ORD-005 | Welding | M-04 | OP-08 | 3600 | 4068 | 468 | Yes
ORD-005 | Assembly | M-05 | OP-08 | 4200 | 4326 | 126 | Yes
ORD-005 | Finishing | M-06 | OP-02 | 1800 | 1854 | 54 | No
ORD-006 | Cutting | M-02 | OP-05 | 1920 | 1977.6 | 57.6 | No
ORD-006 | Welding | M-04 | OP-03 | 2880 | 2880 | 0 | No
ORD-006 | Assembly | M-05 | OP-07 | 3360 | 3360 | 0 | No
ORD-006 | Finishing | M-06 | OP-03 | 1440 | 1440 | 0 | No
ORD-007 | Cutting | M-01 | OP-08 | 1080 | 1090.8 | 10.8 | No
ORD-007 | Welding | M-04 | OP-04 | 1620 | 1636.2 | 16.2 | No
ORD-007 | Assembly | M-05 | OP-04 | 1890 | 1927.8 | 37.8 | No
ORD-007 | Finishing | M-06 | OP-02 | 810 | 822.15 | 12.15 | No
ORD-008 | Cutting | M-01 | OP-04 | 1200 | 1200 | 0 | No
ORD-008 | Welding | M-04 | OP-01 | 1800 | 1782 | -18 | No
ORD-008 | Assembly | M-05 | OP-07 | 2100 | 2058 | -42 | No
ORD-008 | Finishing | M-06 | OP-02 | 900 | 882 | -18 | No
ORD-009 | Cutting | M-02 | OP-01 | 2700 | 2835 | 135 | Yes
ORD-009 | Welding | M-03 | OP-06 | 4050 | 4495.5 | 445.5 | Yes
ORD-009 | Assembly | M-05 | OP-08 | 4725 | 4866.75 | 141.75 | Yes
ORD-009 | Finishing | M-06 | OP-08 | 2025 | 2085.75 | 60.75 | Yes
ORD-010 | Cutting | M-02 | OP-03 | 2100 | 2142 | 42 | No
ORD-010 | Welding | M-04 | OP-03 | 3150 | 2992.5 | -157.5 | No
ORD-010 | Assembly | M-05 | OP-05 | 3675 | 3601.5 | -73.5 | No
ORD-010 | Finishing | M-06 | OP-08 | 1575 | 1575 | 0 | No
ORD-011 | Cutting | M-02 | OP-08 | 1920 | 1881.6 | -38.4 | No
ORD-011 | Welding | M-03 | OP-07 | 2880 | 2966.4 | 86.4 | Yes
ORD-011 | Assembly | M-05 | OP-04 | 3360 | 3376.8 | 16.8 | No
ORD-011 | Finishing | M-06 | OP-06 | 1440 | 1440 | 0 | No
ORD-012 | Cutting | M-02 | OP-07 | 4320 | 4622.4 | 302.4 | Yes
ORD-012 | Welding | M-04 | OP-07 | 6480 | 7257.6 | 777.6 | Yes
ORD-012 | Assembly | M-05 | OP-04 | 7560 | 7938 | 378 | Yes
ORD-012 | Finishing | M-06 | OP-02 | 3240 | 3337.2 | 97.2 | Yes
ORD-013 | Cutting | M-02 | OP-04 | 900 | 918 | 18 | No
ORD-013 | Welding | M-04 | OP-04 | 1350 | 1363.5 | 13.5 | No
ORD-013 | Assembly | M-05 | OP-05 | 1575 | 1543.5 | -31.5 | No
ORD-013 | Finishing | M-06 | OP-07 | 675 | 664.875 | -10.125 | No
ORD-014 | Cutting | M-02 | OP-06 | 960 | 998.4 | 38.4 | No
ORD-014 | Welding | M-04 | OP-08 | 1440 | 1411.2 | -28.8 | No
ORD-014 | Assembly | M-05 | OP-01 | 1680 | 1663.2 | -16.8 | No
ORD-014 | Finishing | M-06 | OP-08 | 720 | 709.2 | -10.8 | No
ORD-015 | Cutting | M-02 | OP-06 | 1440 | 1440 | 0 | No
ORD-015 | Welding | M-04 | OP-04 | 2160 | 2332.8 | 172.8 | Yes
ORD-015 | Assembly | M-05 | OP-02 | 2520 | 2620.8 | 100.8 | Yes
ORD-015 | Finishing | M-06 | OP-05 | 1080 | 1101.6 | 21.6 | No
ORD-016 | Cutting | M-02 | OP-05 | 2100 | 2058 | -42 | No
ORD-016 | Welding | M-03 | OP-04 | 3150 | 3276 | 126 | Yes
ORD-016 | Assembly | M-05 | OP-01 | 3675 | 3748.5 | 73.5 | Yes
ORD-016 | Finishing | M-06 | OP-07 | 1575 | 1575 | 0 | No
ORD-017 | Cutting | M-02 | OP-01 | 1728 | 1693.44 | -34.56 | No
ORD-017 | Welding | M-03 | OP-07 | 2592 | 2695.68 | 103.68 | Yes
ORD-017 | Assembly | M-05 | OP-03 | 3024 | 3084.48 | 60.48 | Yes
ORD-017 | Finishing | M-06 | OP-02 | 1296 | 1257.12 | -38.88 | No
ORD-018 | Cutting | M-04 | OP-01 | 480 | 489.6 | 9.6 | No
ORD-018 | Welding | M-04 | OP-06 | 720 | 806.4 | 86.4 | Yes
ORD-018 | Assembly | M-05 | OP-02 | 840 | 907.2 | 67.2 | Yes
ORD-018 | Finishing | M-06 | OP-03 | 360 | 367.2 | 7.2 | No
ORD-019 | Cutting | M-02 | OP-02 | 4320 | 4363.2 | 43.2 | No
ORD-019 | Welding | M-03 | OP-04 | 6480 | 6544.8 | 64.8 | Yes
ORD-019 | Assembly | M-05 | OP-02 | 7560 | 7333.2 | -226.8 | No
ORD-019 | Finishing | M-06 | OP-06 | 3240 | 3259.44 | 19.44 | No
ORD-020 | Cutting | M-04 | OP-05 | 240 | 254.4 | 14.4 | No
ORD-020 | Welding | M-03 | OP-03 | 360 | 370.8 | 10.8 | No
ORD-020 | Assembly | M-05 | OP-07 | 420 | 432.6 | 12.6 | No
ORD-020 | Finishing | M-06 | OP-06 | 180 | 183.6 | 3.6 | No
ORD-021 | Cutting | M-02 | OP-05 | 3000 | 3150 | 150 | Yes
ORD-021 | Welding | M-03 | OP-03 | 4500 | 4410 | -90 | No
ORD-021 | Assembly | M-05 | OP-05 | 5250 | 5092.5 | -157.5 | No
ORD-021 | Finishing | M-06 | OP-05 | 2250 | 2241 | -9 | No
ORD-022 | Cutting | M-02 | OP-06 | 1200 | 1152 | -48 | No
ORD-022 | Welding | M-04 | OP-03 | 1800 | 1836 | 36 | No
ORD-022 | Assembly | M-05 | OP-05 | 2100 | 2037 | -63 | No
ORD-022 | Finishing | M-06 | OP-02 | 900 | 909 | 9 | No
ORD-023 | Cutting | M-02 | OP-06 | 1800 | 1908 | 108 | Yes
ORD-023 | Welding | M-04 | OP-07 | 2700 | 3051 | 351 | Yes
ORD-023 | Assembly | M-05 | OP-05 | 3150 | 3244.5 | 94.5 | Yes
ORD-023 | Finishing | M-06 | OP-02 | 1350 | 1404 | 54 | Yes
ORD-024 | Cutting | M-02 | OP-03 | 2880 | 2966.4 | 86.4 | Yes
ORD-024 | Welding | M-03 | OP-01 | 4320 | 4276.8 | -43.2 | No
ORD-024 | Assembly | M-05 | OP-02 | 5040 | 4989.6 | -50.4 | No
ORD-024 | Finishing | M-06 | OP-02 | 2160 | 2095.2 | -64.8 | No
ORD-025 | Cutting | M-02 | OP-04 | 720 | 748.8 | 28.8 | No
ORD-025 | Welding | M-04 | OP-08 | 1080 | 1198.8 | 118.8 | Yes
ORD-025 | Assembly | M-05 | OP-02 | 1260 | 1323 | 63 | Yes
ORD-025 | Finishing | M-06 | OP-03 | 540 | 567 | 27 | No
ORD-026 | Cutting | M-02 | OP-05 | 480 | 470.4 | -9.6 | No
ORD-026 | Welding | M-04 | OP-03 | 720 | 734.4 | 14.4 | No
ORD-026 | Assembly | M-05 | OP-07 | 840 | 823.2 | -16.8 | No
ORD-026 | Finishing | M-06 | OP-04 | 360 | 349.2 | -10.8 | No
ORD-027 | Cutting | M-02 | OP-03 | 1800 | 1764 | -36 | No
ORD-027 | Welding | M-03 | OP-04 | 2700 | 2781 | 81 | Yes
ORD-027 | Assembly | M-05 | OP-07 | 3150 | 3213 | 63 | Yes
ORD-027 | Finishing | M-06 | OP-03 | 1350 | 1282.5 | -67.5 | No
ORD-028 | Cutting | M-02 | OP-07 | 1440 | 1497.6 | 57.6 | No
ORD-028 | Welding | M-03 | OP-01 | 2160 | 2268 | 108 | Yes
ORD-028 | Assembly | M-05 | OP-01 | 2520 | 2570.4 | 50.4 | Yes
ORD-028 | Finishing | M-06 | OP-01 | 1080 | 1123.2 | 43.2 | No
ORD-029 | Cutting | M-02 | OP-01 | 3000 | 3030 | 30 | No
ORD-029 | Welding | M-03 | OP-06 | 4500 | 4680 | 180 | Yes
ORD-029 | Assembly | M-05 | OP-07 | 5250 | 5355 | 105 | Yes
ORD-029 | Finishing | M-06 | OP-02 | 2250 | 2182.5 | -67.5 | No
ORD-030 | Cutting | M-02 | OP-01 | 1800 | 1836 | 36 | No
ORD-030 | Welding | M-03 | OP-04 | 2700 | 2916 | 216 | Yes
ORD-030 | Assembly | M-05 | OP-04 | 3150 | 3244.5 | 94.5 | Yes
ORD-030 | Finishing | M-06 | OP-02 | 1350 | 1390.5 | 40.5 | No

## machines
machine_id | machine_type | availability_pct | failure_rate_pct | maintenance_type
M-01 | Cutting Machine | 95 | 2 | Preventive
M-02 | Cutting Machine | 92 | 3 | Preventive
M-03 | Welding Station | 85 | 8 | Corrective
M-04 | Welding Station | 80 | 10 | Corrective
M-05 | Assembly Line | 88 | 6 | Preventive
M-06 | Finishing Unit | 97 | 1 | Preventive

## operators
operator_id | shift | experience_years
OP-01 | Morning | 5
OP-02 | Morning | 3
OP-03 | Afternoon | 7
OP-04 | Afternoon | 2
OP-05 | Night | 10
OP-06 | Night | 4
OP-07 | Morning | 6
OP-08 | Afternoon | 1

## KPIs
Etiquetas de fila | Suma de delay_min
Assembly | 1000.23
Cutting | 1370.04
Finishing | 211.635
Welding | 3762.18
Total general | 6344.085
Etiquetas de fila | Suma de delay_min
M-01 | 152.4
M-02 | 1193.64
M-03 | 1548.18
M-04 | 2238
M-05 | 1000.23
M-06 | 211.635
Total general | 6344.085
Etiquetas de fila | Cuenta de rework
Assembly | 30
No | 16
Yes | 14
Cutting | 30
No | 23
Yes | 7
Finishing | 30
No | 27
Yes | 3
Welding | 30
No | 13
Yes | 17
Total general | 120